Project Planning Phase – Product Backlog, Sprint Planning & Estimation

AI StudyBuddy – AI Assistant for Smarter Learning and Study Support

| Date | 30 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-2273 |
| Project Name | AI StudyBuddy – AI Assistant for Smarter Learning and Study Support |
| Team | Leader: KISHORE.T; Members: LOGESH.D, MANIKANDAN.M, MOHAMED SAFIR.M |

# 1. Project Planning Overview

AI StudyBuddy is planned as a modular AI-assisted learning platform. The backlog below converts the documented project features into actionable Scrum user stories. The project documentation identifies registration/login, study-material upload, AI summaries, flashcards, quizzes, study plans, saved resources and administration as the core workflow.

| Sprint | Epic | Story ID | User Story / Task | Story Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Authentication & User Management | USN-01 | As a student, I can register with name, email and password so that I can create an account. | 3 | High | KISHORE.T |
| Sprint-1 | Authentication & User Management | USN-02 | As a student, I can log in and receive a JWT token so that I can access protected features. | 3 | High | LOGESH.D |
| Sprint-1 | Authentication & User Management | USN-03 | As the system, I can hash passwords with bcrypt so that credentials are not stored in plain text. | 2 | High | LOGESH.D |
| Sprint-1 | Authentication & User Management | USN-04 | As an administrator, I can access protected administrative routes using role-based authorization. | 3 | Medium | KISHORE.T |
| Sprint-1 | Backend Foundation | USN-05 | As a developer, I can configure Express, environment variables, CORS and MongoDB connection. | 3 | High | MANIKANDAN.M |
| Sprint-2 | Study Material Management | USN-06 | As a student, I can upload permitted study files so that they can be processed by the AI features. | 3 | High | MOHAMED SAFIR.M |
| Sprint-2 | Study Material Management | USN-07 | As a student, I can view and manage my stored study materials. | 3 | High | LOGESH.D |
| Sprint-2 | AI Summary | USN-08 | As a student, I can generate a concise summary from my study material. | 3 | High | MANIKANDAN.M |
| Sprint-2 | AI Integration | USN-09 | As the system, I can send study content to the Gemini API and return generated content safely. | 3 | High | KISHORE.T |
| Sprint-3 | AI Flashcards | USN-10 | As a student, I can generate flashcards from study material for active recall. | 3 | High | MOHAMED SAFIR.M |
| Sprint-3 | AI Quiz | USN-11 | As a student, I can generate a multiple-choice quiz from study material. | 3 | High | MANIKANDAN.M |
| Sprint-3 | AI Study Plan | USN-12 | As a student, I can generate a personalized study plan based on goals, available time and exam date. | 5 | High | KISHORE.T |
| Sprint-3 | Saved Resources | USN-13 | As a student, I can retrieve previously generated learning resources. | 3 | Medium | LOGESH.D |
| Sprint-4 | Administration | USN-14 | As an administrator, I can view and manage registered users and monitor system activity. | 3 | Medium | KISHORE.T |
| Sprint-4 | Testing & Quality | USN-15 | As a developer, I can test REST APIs for positive and negative scenarios using Postman/Thunder Client. | 3 | High | MANIKANDAN.M |
| Sprint-4 | Security & Release | USN-16 | As a system owner, I can keep secrets in environment variables and protect private routes. | 3 | High | MOHAMED SAFIR.M |
| Sprint-4 | Documentation | USN-17 | As the project team, we can document setup, architecture, APIs and usage for handover. | 2 | Medium | ALL MEMBERS |

# 2. Sprint Schedule

| Sprint | Total Story Points | Start | End | Scope | Planned Completed | Release |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 28 | 01 Oct 2026 | 07 Oct 2026 | Authentication, backend foundation and database connection | 28 | 07 Oct 2026 (planned) |
| Sprint-2 | 25 | 08 Oct 2026 | 14 Oct 2026 | Study-material upload/management and AI summary | 25 | 14 Oct 2026 (planned) |
| Sprint-3 | 31 | 15 Oct 2026 | 21 Oct 2026 | Flashcards, quiz, study plan and saved resources | 31 | 21 Oct 2026 (planned) |
| Sprint-4 | 16 | 22 Oct 2026 | 28 Oct 2026 | Admin functions, testing, security hardening and documentation | 16 | 28 Oct 2026 (planned) |

# 3. Velocity & Estimation

Using the planned backlog above, the total estimated effort is 100 story points across four 7-day sprints. The planned average velocity is therefore 25 story points per sprint. This is a planning estimate, not a measured historical velocity.

Average planned velocity = 100 story points ÷ 4 sprints = 25 story points/sprint.

Average daily planned capacity = 25 ÷ 7 ≈ 3.57 story points/day.

# 4. Definition of Done

• Code is implemented in the appropriate module (routes, controllers, middleware, models or utilities).

• Protected endpoints verify JWT authentication and required roles.

• Database operations are validated through Mongoose schemas.

• AI endpoints handle Gemini API requests and errors without exposing secrets.

• The API is tested with positive and negative scenarios.

• Documentation and relevant screenshots/results are updated before sprint closure.